PARADISEC Sydney Staff Meeting

Room 238, Transient Building F12, University of Sydney

1 June 2010, 3pm

Present: Aidan Wilson, Linda Barwick, Amanda Harris

1. LIEF report (LB)

LIEF application has gone in, LB thinks it was a good application and meets the criteria that the ARC are looking for in the LIEF scheme.  The application includes: 

upgrading the Quadriga system ($56,000) – this may need to include a service contract since Aidan will no longer be around.

The metadata management will be moved to Melbourne on EOPAS server to be managed by Sylvia.  This will replace the ACL catalogue and will be able to incorporate video.

Sydney will get a full-time audio archiving position and a 4-day project management & curation job.

ANU will get an upgrade of the digital repository.

The content will include the Wurm collection at ANU, Aaron Corn’s materials, Catherine Ingrahm in Melbourne with annotations and linking the Roessler images with audio time codings.

2. Current jobs review

Jadran Mimica’s collection has been finalised, Aidan is about to return it to him and payment has been received.

SWALSC – Diego has digitised all videos but the hard drive needs reformatting.  ACTION: AH to write to Diego about the hard drive.  SWALSC have chosen not to have the commercial film reels digitised, ACTION: AH to search Film Australia and the Sound and Film Archive to see whether copies of these films are available.  The Betacam videos will be taken to Canberra by Jane Simpson next week. ACTION: AW will order 2 more hard drives next week for backup and also extra storage for the video mac. Aidan suggested we put a .exe for installing Quicktime on the hard drive to make sure that all files can be read. ACTION: AH will ask whether they want to organise the courier to return hard drive and originals or whether we should organise it – we can use the packing containers to return everything.

Wollongong: there are 40-50 reels to be processed, ACTION: AH H will call Steve to confirm a time to get the back-up machine and offer to pre-pay 3 weeks upfront – cash transfer if necessary (or preferably CC).  When we have the machine, AH will write to Noel to arrange the hard drive transfer. 

Martin Thomas Materials: there is $2000 in the budget for Paradisec overheads, Aidan suggested we put a .exe for installing Quicktime on the hard drive to make sure that all files can be read. ACTION: LB will find some documentation of the grant budget containing the $2000 and AH will request a journal transfer from A7568 to 11111. Aidan suggested we put a .exe for installing Quicktime on the hard drive to make sure that all files can be read. ACTION: AH will request a new contract for Diego for 100 hours.

Poetry tapes: have been digitised, Aidan is waiting for UCC to free up some space to transfer the files. ACTION: Once we have the new hard drives, AW will transfer Kathy Marsh’s materials onto them to free up Azoulay space.

ACTION: AW will write to Steve Darlo and request that initially 1TB and eventually 2TB be made available to us.

3. Dataflow from ANU and Melbourne

Julia is processing material but it is not yet being sent to Sydney.  LB suggested we need staging space to cope with remote ingestion.  LB suggested there might be a way to stop uploading until related metadata has been entered into the catalogue.

4. Azoulay virtualisation

ACTION: AW will write to Steve Darlo to escalate virtualising the server and processing functions. ACTION: AW to prepare a one-page account of what will happen with the new server setup for the meeting.

5. Visit from Julia

ACTION: AH will give Julia a mini-catalogue training session before the meeting. ACTION: AH to ask Julia to bring metadata and files on a hard drive and set up a Skype chat with Darrell.  AH will also give her suggestions of where to stay and ask whether she can get here by 9:30 Monday for Mon/Tues

6. Anything else needed to prepare for "real" meeting next week
ACTION: AH will arrange for Nick’s 11111 contract date to be extended.
